ספר המסמכים המלא — TaskFlow: מהרעיון עד ה-Launch

מטרת המסמך: זהו קובץ ייחוס מקיף המכיל את כל המסמכים שנכתבו במהלך מחזור חיים מלא של מוצר טכנולוגי — מהרעיון הראשוני ועד לאחר ה-Launch. כל מסמך מוצג עם תוכנו המלא, בעל מי כותב אותו, ולמי הוא מיועד.

📋 מדריך המסמכים לפי שלב

| שלב | מסמכים מרכזיים | מי כותב | משך |
| --- | --- | --- | --- |

| 1. Ideation | Product Brief, Research Report, Competitive Analysis | PM, UX Research, Marketing | 2–4 שב' |
| --- | --- | --- | --- |
| 2. Budget Approval | Business Case, Budget Request, Risk Register | PM, Finance, Engineering | 1–2 שב' |
| 3. Requirements | PRD, BRD, SRS, FRD, ADR | PM, Engineering, Legal | 3–4 שב' |
| 4. Design | Design Spec, UX Research Report, TDD | Designer, Engineering | 3–4 שב' |
| 5. Development | Sprint Plans, Definition of Done, Code Review Checklist | Engineering, PM | 8–12 שב' |
| 6. QA & Testing | Test Plan, Test Cases, Bug Report, UAT Report | QA, PM | 3–4 שב' |
| 7. Security | Threat Model, SSDLC Review, Penetration Test Report | Security, Engineering | 2–3 שב' |
| 8. Legal & Compliance | Privacy Policy, DPA, IP Assignment, NDA | Legal, PM | 2–3 שב' |
| 9. Launch | Go-Live Checklist, Runbook, GTM Doc, Launch Brief | All Departments | 1–2 שב' |
| 10. Post-Launch | Post-Mortem, OKR Review, Roadmap Update | PM, Engineering | 1–2 שב' |

שלב 1: גיבוש הרעיון והיוזמה (Ideation & Discovery)

📄 מסמך 1.1 — Product Brief ראשוני

כותב: Product Manager
מיועד ל: CEO, CTO, VP Product, Design Lead
מתי: ימים 1–5 של הפרויקט

TaskFlow — Product Brief v0.1
תאריך: יום 1 | סטטוס: Draft לדיון

1. הבעיה שאנחנו פותרים

ב-SaaS בי-בי, צוותי Customer Success מבלים בממוצע 4–6 שעות שבועיות במעקב ידני אחרי Tasks בין מחלקות. המידע מפוצל בין Jira, Slack, ואימיילים, ואין Handoff מובנה כאשר Task עוברת בין אחריות של מחלקה אחת לאחרת. כתוצאה מכך, 34% מה-Tasks "נופלים בין הכיסאות" לפי הנתונים הפנימיים שלנו מ-Q3.

2. הפתרון המוצע (High Level)

מערכת ניהול Tasks המשולבת ב-Slack שמאפשרת Handoff אוטומטי בין מחלקות, עם Dashboard ויזואלי ומנוע תזכורות חכם.

3. מי המשתמשים

- Customer Success Manager (משתמש ראשי)

- Team Lead / Manager (Dashboard ומעקב)

- Operations / Finance (אינטגרציה עם מערכות קיימות)

4. למה עכשיו?

שלושה לקוחות ביקשו פתרון זה ב-Q3 Reviews האחרונים. המתחרה Asana השיקה פיצ'ר דומה ב-Limited Beta.

5. מה אנחנו לא בונים (Out of Scope v1)

- אינטגרציה עם ERP

- Mobile App

- AI Prioritization

6. הצלחה נראית כך

- 50% ירידה בזמן המעקב הידני

- Adoption של 80% מהצוות ב-30 יום מ-Launch

- NPS > 40

7. שאלות פתוחות לסגירה

- האם לבנות כ-Slack App בלבד או גם Web Dashboard?

- מה מודל הרישוי? Per Seat? Per Organization?

- האם Phase 1 כולל גם Reporting?

📄 מסמך 1.2 — User Research Report

כותב: UX Researcher
מיועד ל: PM, Design Lead, Engineering Lead
מתי: ימים 5–14

TaskFlow — User Research Report v1.0
מתודולוגיה: 12 ראיונות עומק (45 דקות כל אחד) + 3 Session Recordings מהמוצר הקיים

Participant Profile

| # | תפקיד | חברה | גודל צוות |
| --- | --- | --- | --- |
| P1 | CSM Lead | SaaS B2B | 120 עובדים |
| P2 | Team Lead, Ops | E-commerce | 45 עובדים |
| P3 | VP CS | FinTech | 300 עובדים |
| P4-P12 | CS Reps, Managers | Mixed | 50–500 |

ממצאים מרכזיים

Pain Point #1 — הכאב הגדול ביותר: "אני לא יודע מי אחראי עכשיו"

"כשאני מעבירה Task לאופרציה, אני שולחת Slack, אימייל, ומוסיפה ב-Jira. ואז אני מחכה. ולפעמים שוכחת לחכות." — P1, CSM Lead

"הבעיה היא לא שאנשים לא עושים את העבודה. הבעיה שאנחנו לא יודעים מה סטטוס הדברים ברגע הנתון." — P3, VP CS

Pain Point #2 — Context נאבד ב-Handoff

"כשהTask מגיעה אלי, אני מקבל 'תטפל בזה' בלי שום רקע. אני צריך ל-chase אחרי המידע." — P7, Operations Rep

Pain Point #3 — אין Accountability ברורה

34% מהמשתתפים ציינו שנפלו בין כיסאות לפחות 3 פעמים בחודש האחרון.

Empathy Map — Sarah, CSM Lead

| What she THINKS | What she FEELS |
| --- | --- |
| "הכלים לא מדברים אחד עם השני" | Frustrated, overwhelmed |
| "אני עושה עבודה של Coordinator" | Undervalued |
| What she SAYS | What she DOES |
| -------------- | --------------- |
| "שלחתי לך Slack" | Creates manual spreadsheet tracker |
| "תוודא שהOps קיבלו" | Sends duplicate messages |

Job-to-be-Done (Primary)

"When I need to hand off a task to another team, I want to know it's been received, understood, and is being tracked — so I can move on without worrying it'll fall through."

Job-to-be-Done (Secondary)

"When my manager asks about task status, I want to give an immediate, accurate answer — so I look on top of things."

המלצות לעיצוב מהמחקר

- Handoff חייב להיות One-Click — לא פורמה ארוכה

- Status Update אוטומטי — לא דורש action מהמשתמש

- Context Bundle — כל הקשר מועבר אוטומטית עם ה-Task

- Notification חכמה — לא flood של עדכונים, רק מה שחשוב

📄 מסמך 1.3 — Competitive Analysis Report

כותב: Product Marketing Manager
מיועד ל: PM, CEO, Sales
מתי: ימים 7–14

TaskFlow — Competitive Analysis v1.0

מתחרים ישירים

| מוצר | נקודות חוזק | נקודות חולשה | מחיר | Share |
| --- | --- | --- | --- | --- |
| Asana | UI מעולה, Integrations רבות | אין Slack-Native, יקר | $10.99/user | 35% |
| Monday.com | Customization גבוה, Visual | מורכב מדי לCSM, לא Slack-first | $9/user | 28% |
| ClickUp | Feature-rich, מחיר נמוך | Overwhelming, Slow performance | $5/user | 18% |
| Linear | Engineering-focused, מהיר | לא מתאים ל-CS Teams | $8/user | 9% |

Positioning Gap שזיהינו

אין מוצר שמשלב: (1) Slack-Native, (2) Cross-Department Handoff, (3) מיועד לCS/Ops Teams, (4) מחיר Mid-Market. זהו ה-White Space שלנו.[1][2]

ICP (Ideal Customer Profile)

- SaaS B2B, 50–500 עובדים

- יש Team CS + Ops נפרד (לפחות 2 מחלקות)

- משתמשים ב-Slack כ-Primary Communication

- נכאב מ-Handoff בין מחלקות

שלב 2: אישור תקציב ומשאבים

📄 מסמך 2.1 — Business Case Document

כותב: PM + Finance Partner
מיועד ל: CFO, CEO, Board
מתי: ימים 15–21

TaskFlow — Business Case v1.0
סטטוס: Pending CFO Approval

Executive Summary

פיתוח TaskFlow — מוצר Slack-Native לניהול Cross-Department Handoffs — מהווה הזדמנות הכנסה של 2.4M$ ARR בשנה 2 (Conservative) עד 5.1M$ ARR (Optimistic), עם השקעה כוללת של 680K$ ב-12 חודשים הראשונים. ה-Payback Period הצפוי: 14–18 חודשים.

1. Investment Summary

| קטגוריה | עלות שנה 1 | הערות |
| --- | --- | --- |
| Engineering (4 FTEs) | 480,000$ | 2 Backend, 1 Frontend, 1 QA |
| Design (1 FTE + Contractor) | 120,000$ | 0.5 FTE + 60K$ contractor |
| Infrastructure (AWS) | 36,000$ | Staging + Production |
| Security Audit | 25,000$ | External Pen Test |
| Legal & Compliance | 18,000$ | GDPR, IP Review |
| Marketing (GTM) | 45,000$ | Launch Campaign |
| סה"כ | 724,000$ |  |

2. Revenue Projections

| תרחיש | שנה 1 ARR | שנה 2 ARR | שנה 3 ARR |
| --- | --- | --- | --- |
| Conservative | 480K$ | 1.9M$ | 3.8M$ |
| Base | 720K$ | 2.4M$ | 5.1M$ |
| Optimistic | 1.1M$ | 4.2M$ | 8.9M$ |

הנחות: $29/org/month, 10% conversion מ-Free Trial, CAC $420

3. ROI Analysis

- Base Case ROI (Year 2): 231%

- Payback Period: 16 חודשים

- NPV (3 שנים, 10% discount): 4.2M$[3][4][5]

4. Risk Register

| סיכון | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Slack API שינוי | Medium | High | Multi-channel architecture |
| מתחרה משיק קודם | Low | Medium | Fast MVP in 12 weeks |
| Engineering Capacity | Medium | High | Pre-approved hiring plan |
| GDPR Non-Compliance | Low | Very High | Legal review in Sprints 1-2 |

5. Go/No-Go Criteria (Stage Gate)

- Month 3: 50 Beta Users, NPS > 30

- Month 6: 200 Paying Orgs, Churn < 5%

- Month 12: ARR Target ± 20%

📄 מסמך 2.2 — Headcount Request

כותב: HR Business Partner + PM
מיועד ל: CHRO, CFO, Hiring Manager
מתי: ימים 18–25

TaskFlow — Headcount Request Form

| תפקיד | Seniority | Start Date | Salary Band | סטטוס |
| --- | --- | --- | --- | --- |
| Backend Engineer | Senior | Week 6 | 180–220K$ | Open |
| Backend Engineer | Mid | Week 8 | 140–170K$ | Open |
| Frontend Engineer | Senior | Week 6 | 170–210K$ | Open |
| QA Engineer | Mid | Week 10 | 120–150K$ | Pending |
| UX/UI Designer (Contract) | Senior | Week 4 | 85$/hr | Open |

Hiring Timeline (Estimated)

- Time to Hire: 6–10 שבועות לכל תפקיד

- Onboarding + Ramp: 4 שבועות נוספות

- Total Lead Time: 10–14 שבועות[6][7]

שלב 3: דרישות ותכנון (Requirements & Planning)

📄 מסמך 3.1 — PRD (Product Requirements Document)

כותב: Product Manager
מיועד ל: Engineering, Design, QA, Marketing, Legal
מתי: ימים 22–35 | גרסה חיה לאורך כל הפרויקט

TaskFlow — PRD v1.3
Owner: Maya Cohen (PM) | Last Updated: Week 4 | Status: Approved

1. Problem Statement

CS Teams in B2B SaaS companies lose 4–6 hours/week tracking cross-department task handoffs. 34% of tasks fall through because there's no standardized handoff mechanism between teams using different tools (Jira, Slack, email).

2. Goals & Success Metrics

| מטרה | KPI | Target |
| --- | --- | --- |
| הפחתת זמן מעקב | Hours/week on tracking | מ-5.2 ל-2.0 |
| Handoff Reliability | % Tasks tracked end-to-end | 95%+ |
| Adoption | MAU / Total Users | 80%+ |
| Satisfaction | NPS | >40 |

3. User Personas

Sarah — CSM Lead (Primary)

- 5 שנות ניסיון, מנהלת 50 חשבונות

- משתמשת ב-Slack כל יום, Jira לעיתים רחוקות

- Motivation: לסגור Tasks מהר ולעמוד ב-SLA

Tom — Operations Manager (Secondary)

- מקבל Handoffs מ-5 מחלקות שונות

- רוצה תעדוף ברור ו-Context מלא

- Pain: "אני מקבל Slack מבלי שום פרטים"

4. Feature Scope — MoSCoW

Must Have (v1)

- [ ] יצירת Task ב-Slack (Command: /task)

- [ ] Handoff בין משתמשים / מחלקות

- [ ] Status Tracking (Open → In Progress → Done)

- [ ] Email + Slack Notification על שינוי סטטוס

- [ ] Web Dashboard — My Tasks + Team Tasks

- [ ] Audit Trail מלא לכל Task

Should Have (v1)

- [ ] Reminder אוטומטי אם Task לא נגע ב-48 שעות

- [ ] Priority Labels (P1/P2/P3)

- [ ] Comment Thread על Task

- [ ] CSV Export

Could Have (v2)

- [ ] AI Priority Suggestion

- [ ] Recurring Tasks

- [ ] Mobile Push Notifications

Won't Have (v1)

- ❌ ERP Integration

- ❌ Custom Fields

- ❌ API Public

- ❌ White Label

5. Functional Requirements

FR-001: Task Creation via Slack

כאשר משתמש מקליד /task create [title]
המערכת תציג Modal ב-Slack עם שדות:
- Title (required, max 200 chars)
- Assigned To (required, user or @channel)
- Due Date (optional)
- Priority (optional, default P2)
- Description (optional, max 1000 chars)
- Attachments (optional, max 5 files, 10MB each)

FR-002: Handoff

כאשר משתמש לוחץ "Handoff" על Task
המערכת תציג בחירת:
- Assign To (user/team)
- Context Note (required, min 10 chars)
- Due Date (required)
לאחר אישור:
- הבעלות עוברת
- Slack DM נשלח לנמען עם כל ה-Context
- Audit Log מתעדכן
- הגורם המעביר מקבל Notification על קבלה

6. Non-Functional Requirements

| דרישה | Target |
| --- | --- |
| Response Time (API) | < 200ms (P95) |
| Availability | 99.9% Uptime |
| Data Encryption | AES-256 at rest, TLS 1.3 in transit |
| GDPR | Data residency EU/US selectable |
| Concurrent Users | 10,000+ |

7. Open Questions

| שאלה | בעלים | Due |
| --- | --- | --- |
| האם Notification ל-Email ב-Default ON? | PM | Week 5 |
| מה קורה ל-Task כש-User עוזב החברה? | Engineering | Week 6 |
| GDPR: כמה זמן שומרים Audit Logs? | Legal | Week 5 | [8][9][10][11] |

📄 מסמך 3.2 — BRD (Business Requirements Document)

כותב: PM + Business Analyst
מיועד ל: Executives, Stakeholders, Legal
מתי: ימים 22–28

TaskFlow — BRD v1.0
High-Level Business Requirements — למי שלא צריך את הפרטים הטכניים

Business Objective

בניית מוצר SaaS חדש שמאפשר ניהול Tasks Cross-Department דרך Slack, עם מטרה עסקית להגיע ל-ARR של 2.4M$ תוך 24 חודשים.

Stakeholders

| Stakeholder | עניין עיקרי | רמת מעורבות |
| --- | --- | --- |
| CEO | Business Growth, Market Share | High — אישור Stage Gates |
| CTO | Technical Feasibility, Architecture | High — אישור טכני |
| CFO | ROI, Budget Control | Medium — Monthly Review |
| VP Sales | Positioning, Pricing | Medium — Launch Review |
| Legal | IP, GDPR, Contracts | Low-Medium — Phase Reviews |

Business Constraints

- Launch תוך 9 חודשים (Board Commitment)

- Budget Cap: 750K$ שנה 1

- GDPR Compliance חובה לפני Launch

- לא מחליף מוצרים קיימים (Integration Only)

Success Criteria

- 200 Paying Organizations תוך 6 חודשים מ-Launch

- Churn < 5% חודשי

- Support Ticket Rate < 2% מה-MAU[12][13]

📄 מסמך 3.3 — SRS (Software Requirements Specification)

כותב: Engineering Lead + PM
מיועד ל: Engineering Team, QA, Security
מתי: ימים 28–40

TaskFlow — SRS v1.0
IEEE 830 Format — Technical Requirements Document

1. System Overview

TaskFlow הוא מערכת Web + Slack App המורכבת מ:

- Slack Bot (Node.js)

- REST API + GraphQL (Node.js/TypeScript)

- Web Dashboard (React)

- Database (PostgreSQL + Redis)

- Infrastructure (AWS: ECS, RDS, ElastiCache, S3)

2. External Interfaces

2.1 Slack API

- Events API (Webhooks)

- Block Kit UI

- OAuth 2.0 for Workspace Authentication

- Rate Limits: 1 message/second per channel

2.2 Email

- Provider: SendGrid

- Transactional Templates

- Unsubscribe Management (CAN-SPAM + GDPR)

3. Functional Requirements

3.1 Authentication

- Single Sign-On via Slack OAuth

- Optional: Google OAuth, SAML (v2)

- Session timeout: 8 hours (configurable)

- MFA: Optional in v1, Required for Admin in v2

3.2 Data Model

Task {
  id: UUID
  title: string (max 200)
  description: text (max 1000)
  status: enum(OPEN, IN_PROGRESS, BLOCKED, DONE, ARCHIVED)
  priority: enum(P1, P2, P3)
  created_by: UserID
  assigned_to: UserID
  department: DepartmentID
  created_at: timestamp
  updated_at: timestamp
  due_date: date (nullable)
  slack_message_ts: string (nullable)
  audit_log: AuditEntry[]
}

AuditEntry {
  id: UUID
  task_id: UUID
  user_id: UUID
  action: enum(CREATED, UPDATED, ASSIGNED, HANDOFF, COMMENTED, COMPLETED)
  timestamp: timestamp
  details: jsonb
}

4. Non-Functional Requirements

4.1 Performance

- API Response < 200ms (P95), < 500ms (P99)

- Dashboard Load < 2 seconds (FCP)

- Slack Bot Response < 3 seconds

4.2 Scalability

- 10,000 concurrent users (MVP target)

- 1M Tasks in DB without performance degradation

- Horizontal scaling via ECS Auto Scaling

4.3 Security

- OWASP Top 10 compliance

- Penetration Test לפני Launch

- SOC 2 Type I roadmap (Year 2)

- Data Encryption: AES-256 at rest, TLS 1.3

4.4 Compliance

- GDPR: Right to Erasure implemented

- Data Residency: EU/US selectable at Org level

- Audit Logs retention: 2 years minimum[14][15][13][12]

📄 מסמך 3.4 — ADR (Architecture Decision Record)

כותב: Engineering Lead
מיועד ל: Engineering Team, Future Engineers
מתי: ימים 28–40

ADR-001: בחירת Database — PostgreSQL

תאריך: Week 4 | סטטוס: Accepted

Context

צריכים DB שתומך ב-JSONB (Audit Logs), מעולה ב-Relational Queries, ויש Managed Service ב-AWS (RDS).

Options Considered

| אפשרות | יתרונות | חסרונות |
| --- | --- | --- |
| PostgreSQL | JSONB, ACID, RDS, Mature | Scaling Complex Tasks |
| MySQL | Familiar, Fast Reads | JSONB Support חלש |
| DynamoDB | Scale | Queries מורכבות קשות, עלות |

Decision: PostgreSQL עם AWS RDS
Consequences: יצטרכו Migration מורכב אם Scale > 100M Tasks (אבל לא בעיה ל-MVP)

ADR-002: Slack-First vs. Multi-Channel

תאריך: Week 4 | סטטוס: Accepted

Context

Marketing רצתה גם MS Teams. Engineering אמרה שזה מכפיל את הזמן.

Decision: Slack בלבד ל-v1. Architecture Abstraction Layer שיאפשר Teams ב-v2 ללא Rewrite.

Consequences: v2 Teams support זול יותר ב-60%, v1 מהיר יותר ב-3 חודשים.

ADR-003: Monolith vs. Microservices

תאריך: Week 5 | סטטוס: Accepted

Decision: Modular Monolith ל-v1 עם Bounded Contexts ברורים. פיצול ל-Microservices אם MAU > 50K.

Reasoning: הצוות קטן (4 engineers). Microservices Overhead גדול מדי בשלב זה.[16][17][18]

שלב 4: עיצוב ואדריכלות

📄 מסמך 4.1 — Design Specification

כותב: UX/UI Designer + PM
מיועד ל: Engineering, PM, QA
מתי: ימים 36–55

TaskFlow — Design Spec v1.0
Figma Link: [figma.com/taskflow-v1] | Status: Approved by PM

Design System

Colors

Primary:    #2D5BFF (Blue)    — CTAs, Links, Active States
Secondary:  #1A1A2E (Dark)    — Text, Headers
Success:    #10B981 (Green)   — Done Status, Confirmations
Warning:    #F59E0B (Amber)   — Reminders, Blocked Status
Danger:     #EF4444 (Red)     — Errors, P1 Tasks
Background: #F8FAFC           — App Background
Surface:    #FFFFFF           — Cards, Modals

Typography

Font: Inter (Google Fonts)
H1: 32px / 700 weight
H2: 24px / 600 weight
H3: 20px / 600 weight
Body: 16px / 400 weight
Small: 14px / 400 weight
Caption: 12px / 400 weight

Component Inventory

| Component | States | Notes |
| --- | --- | --- |
| Task Card | Default, Hover, Selected, Overdue | Drag & Drop ב-v2 |
| Handoff Button | Default, Loading, Success | One-click |
| Status Badge | Open, In Progress, Blocked, Done | Color coded |
| Priority Tag | P1 (Red), P2 (Amber), P3 (Grey) |  |
| User Avatar | Active, Away, Offline | Slack Status |

Key Screens — Annotations

Screen 1: Web Dashboard — My Tasks

- Header: Filter (Status, Priority, Department, Date)

- Task List: Sorted by Due Date Default

- Right Panel: Task Detail on Click

- FAB: "+ New Task" (Fixed Bottom Right)

- Empty State: Illustration + CTA "Create your first task"

Screen 2: Slack Modal — Task Creation

- Block Kit Form

- Required fields clearly marked (*)

- Inline Validation (not submit-time)

- "Cancel" closes without saving

Screen 3: Handoff Flow

- Step 1: Choose recipient (Search by name/team)

- Step 2: Add context note (required, placeholder: "What does the recipient need to know?")

- Step 3: Confirm — Preview of what recipient will receive

- Success: Animated checkmark + "Task handed off to [Name]"

Accessibility Checklist

- [ ] WCAG 2.1 Level AA

- [ ] Keyboard Navigation מלאה

- [ ] Screen Reader Labels על כל Interactive Element

- [ ] Contrast Ratio > 4.5:1

- [ ] Focus Indicators ברורים

שלב 5: פיתוח

📄 מסמך 5.1 — Sprint Planning Document (Sprint 1)

כותב: Engineering Lead + PM
מיועד ל: Engineering Team
מתי: תחילת כל Sprint

TaskFlow — Sprint 1 Planning
Dates: Week 7–8 | Capacity: 60 Story Points | Goal: Authentication + Basic Task CRUD

Sprint Goal

משתמש יכול להתחבר דרך Slack OAuth, ליצור Task בסיסית, ולראות אותה ב-Dashboard.

Sprint Backlog

| Story | Points | Assignee | Status |
| --- | --- | --- | --- |
| TASK-001: Slack OAuth Setup | 8 | Dan (BE) | To Do |
| TASK-002: User Profile Creation | 5 | Dan (BE) | To Do |
| TASK-003: Task Model + API (CRUD) | 13 | Noa (BE) | To Do |
| TASK-004: /task create Command | 8 | Dan (BE) | To Do |
| TASK-005: Web Dashboard — Auth | 5 | Lior (FE) | To Do |
| TASK-006: My Tasks Page (Basic) | 8 | Lior (FE) | To Do |
| TASK-007: Unit Tests (Auth + Task) | 5 | Tom (QA) | To Do |
| TASK-008: Database Migrations | 3 | Dan (BE) | To Do |
| סה"כ | 55 |  |  |

Definition of Done (DoD)

כל Story נחשבת Done רק כאשר:

- [ ] קוד כתוב ו-Pass על כל Unit Tests

- [ ] Code Review אושר ע"י לפחות 1 Reviewer

- [ ] Integration Tests עוברים

- [ ] No Critical/High Bugs פתוחים

- [ ] Deployed ל-Staging

- [ ] PM אישר את הפיצ'ר ב-Staging

- [ ] Documentation עודכנה (API Docs + README)[19][20][21][22]

📄 מסמך 5.2 — Code Review Checklist

כותב: Engineering Lead
מיועד ל: כל המהנדסים
מתי: כל Pull Request

TaskFlow — Code Review Checklist v1.0

Reviewer חייב לבדוק:

Functionality

- [ ] הקוד עושה מה שה-Story ביקשה?

- [ ] Edge Cases מטופלים?

- [ ] Error Handling מתאים?

Security

- [ ] אין Hardcoded Secrets / API Keys

- [ ] Input Validation על כל User Input

- [ ] SQL Queries משתמשים ב-Parameterized Queries (לא String Concatenation)

- [ ] Authorization Check — המשתמש מורשה לבצע הפעולה?

Performance

- [ ] אין N+1 Queries

- [ ] Expensive Operations מ-Cache או Async?

- [ ] Database Indexes מתאימים?

Code Quality

- [ ] Functions קצרות ועושות דבר אחד

- [ ] Variable Names ברורים

- [ ] אין Code Duplication (DRY)

- [ ] Test Coverage > 80%

Documentation

- [ ] Public API Functions מתועדות

- [ ] CHANGELOG עודכן

- [ ] README עודכן אם צריך

שלב 6: QA ובדיקות

📄 מסמך 6.1 — Test Plan

כותב: QA Lead
מיועד ל: Engineering, PM, Management
מתי: ימים 50–60

TaskFlow — Test Plan v1.0

Testing Scope

| סוג בדיקה | כלי | Coverage Target | מי מבצע |
| --- | --- | --- | --- |
| Unit Tests | Jest | 80%+ | Engineers |
| Integration Tests | Supertest | Critical Paths | Engineers |
| E2E Tests | Playwright | 15 Critical Flows | QA |
| Performance | k6 | 10K concurrent | DevOps + QA |
| Security (SAST) | SonarQube | All Code | Security |
| Penetration Test | External Vendor | Pre-Launch | Security |
| UAT | Manual | 5 Beta Customers | PM + QA |

15 Critical E2E Test Cases

| TC# | תרחיש | Expected Result | Priority |
| --- | --- | --- | --- |
| TC-001 | Slack OAuth Login | User authenticated, Dashboard loaded | Critical |
| TC-002 | Create Task via /task | Task appears in Dashboard | Critical |
| TC-003 | Handoff Task to another user | Recipient gets Slack DM, Task reassigned | Critical |
| TC-004 | Task moves to Done | Status updated, Creator notified | High |
| TC-005 | Create Task with missing required field | Inline error shown, Task not created | High |
| TC-006 | Handoff with no Context Note | Validation error shown | High |
| TC-007 | Dashboard filter by Status | Only matching Tasks shown | Medium |
| TC-008 | CSV Export | File downloaded with correct data | Medium |
| TC-009 | 48hr auto-reminder | Slack DM sent to assignee | High |
| TC-010 | P1 Task Overdue | Red badge + Immediate notification | High |
| TC-011 | Delete Task | Task removed, Audit Log entry created | Medium |
| TC-012 | Concurrent users (stress) | < 500ms at 1000 concurrent | Critical |
| TC-013 | Mobile Browser (Responsive) | Dashboard usable on iPhone 14 | Medium |
| TC-014 | GDPR: Delete User Data | All PII removed within 30 days | Critical |
| TC-015 | Audit Log completeness | All actions tracked with user+timestamp | Critical |

Entry / Exit Criteria

- Entry: Code deployed to Staging, Unit Tests all passing

- Exit: 0 Critical bugs, < 3 High bugs, All TC-Critical passing, PM sign-off[23][14]

📄 מסמך 6.2 — Bug Report Template

כותב: QA Engineers
מיועד ל: Engineering, PM
כל Bug ש-QA מוצא

Bug Report — BUG-0047

| שדה | ערך |
| --- | --- |
| Title | Handoff fails silently when recipient is in different Slack Workspace |
| Reporter | Tom (QA) |
| Date | Week 9, Day 3 |
| Severity | HIGH |
| Priority | P1 |
| Status | Open |
| Assigned To | Dan (BE) |
| Sprint | Sprint 3 |

Steps to Reproduce

- Login as User A (Workspace A)

- Create a Task

- Attempt to Handoff to User B (Workspace B)

- Click "Confirm Handoff"

Expected Result

Error message: "Recipient must be in the same Slack Workspace"

Actual Result

Loading spinner appears for 3 seconds, then disappears. Task remains assigned to User A. No error shown to user.

Environment

- Browser: Chrome 121

- OS: macOS 14

- Staging Build: v0.4.2

Attachments

- Screenshot: [bug-0047-screenshot.png]

- Network Log: [bug-0047-network.har]

📄 מסמך 6.3 — UAT Report

כותב: PM + QA
מיועד ל: Stakeholders, Engineering
מתי: שבועות 11–12

TaskFlow — UAT Report v1.0
5 Beta Customers | 2 Weeks Testing | 23 Participants

Overall Results

| מדד | ציון |
| --- | --- |
| Task Completion Rate | 87% |
| Error Rate | 2.3% |
| NPS (Beta) | 34 |
| "Would Recommend" | 78% |

Critical Issues Found

- Handoff notification arrives 15–45 seconds late (Bug-0052 — Fixed)

- Mobile Dashboard unusable on iPhone SE (Bug-0058 — Fixed)

- "Export CSV" exports only visible Tasks, not all (Bug-0061 — Fixed)

User Quotes

"The Handoff flow is exactly what I've been missing. One click and I'm done." — Sarah, CSM Lead, Beta Customer #2

"The reminder is nice but it's too aggressive. Every 24 hours is too much." — Mike, Ops Manager, Beta Customer #4

Action Items from UAT

| פריט | פעולה | בעלים | Due |
| --- | --- | --- | --- |
| Reminder Frequency | הפיכה ל-Configurable (24/48/72hr) | PM + Dev | Sprint 5 |
| Mobile Dashboard | Responsive Fix | Lior (FE) | Sprint 4 |
| CSV Export | Export כל Tasks, לא רק Visible | Tom (BE) | Sprint 4 |

שלב 7: אבטחה ואבטחת מידע

📄 מסמך 7.1 — Threat Model (STRIDE)

כותב: Security Engineer + Engineering Lead
מיועד ל: Engineering, Legal, CTO
מתי: ימים 40–55

TaskFlow — Threat Model v1.0
Framework: STRIDE | Tool: OWASP Threat Dragon

System Components Analyzed

- Slack Bot (Webhook Receiver)

- REST API (Public Facing)

- Web Dashboard (React SPA)

- PostgreSQL Database

- AWS Infrastructure

STRIDE Analysis

| Threat Category | Component | Threat | Mitigation | Status |
| --- | --- | --- | --- | --- |
| Spoofing | Slack Webhook | Attacker sends fake Slack events | Verify Slack Signing Secret on every request | ✅ Mitigated |
| Tampering | API | Attacker modifies Task data in transit | TLS 1.3 mandatory, HSTS headers | ✅ Mitigated |
| Repudiation | Task Actions | User denies performing action | Immutable Audit Log with user+IP+timestamp | ✅ Mitigated |
| Info Disclosure | Database | SQL Injection exposes all Tasks | Parameterized Queries only, no dynamic SQL | ✅ Mitigated |
| DoS | API | Bot floods API with requests | Rate Limiting (100 req/min per IP), AWS WAF | ✅ Mitigated |
| Elevation of Privilege | API | Regular user accesses admin endpoints | RBAC on all endpoints, JWT role claims | ✅ Mitigated |
| Info Disclosure | S3 Attachments | Public access to Task attachments | Private S3, Pre-signed URLs (1hr expiry) | ✅ Mitigated |
| Tampering | JWT | Token Forgery | RS256 signing, token rotation every 8hrs | ✅ Mitigated |

Security Requirements Generated from Threat Model

- [ ] SEC-001: Slack Signing Secret Validation (Priority: Critical)

- [ ] SEC-002: Parameterized Queries Only (Priority: Critical)

- [ ] SEC-003: Rate Limiting 100 req/min/IP (Priority: High)

- [ ] SEC-004: RBAC on all /admin/* endpoints (Priority: Critical)

- [ ] SEC-005: Pre-signed S3 URLs, max 1hr (Priority: High)

- [ ] SEC-006: Immutable Audit Logs (Priority: High)

- [ ] SEC-007: No PII in Application Logs (Priority: High)

- [ ] SEC-008: SAST in CI/CD Pipeline (Priority: Medium)[24][25][26][27]

📄 מסמך 7.2 — Penetration Test Report Summary

כותב: External Security Vendor
מיועד ל: CTO, Engineering Lead, CISO
מתי: שבוע 11

TaskFlow — Pen Test Executive Summary
Vendor: [External Security Firm] | Scope: Web App + API + Slack Integration

Findings Summary

| Severity | Count | Remediated |
| --- | --- | --- |
| Critical | 0 | — |
| High | 2 | 2 (100%) |
| Medium | 5 | 4 (80%) |
| Low | 8 | 3 (37%) |
| Info | 12 | — |

High Findings (Resolved)

H-001: Broken Object Level Authorization

- ה-API לא בדק שהTask שייכת למשתמש המבקש

- כל משתמש מחובר יכול היה לקרוא Tasks של ארגונים אחרים

- Fix: Tenant Isolation Middleware על כל API Route

H-002: JWT Secret Hardcoded in Docker Image

- ה-JWT Secret נמצא ב-Dockerfile ש-Commit לגיטהאב

- Fix: ניוד ל-AWS Secrets Manager, Rotate Secret

שלב 8: משפטי ותאימות

📄 מסמך 8.1 — GDPR Compliance Checklist

כותב: Legal / DPO + Engineering
מיועד ל: CTO, Legal, Management
מתי: ימים 40–65

TaskFlow — GDPR Compliance Checklist

Article 13/14 — Privacy Notice

- [x] Privacy Policy כתובה בשפה ברורה

- [x] Lawful Basis מוגדר (Legitimate Interest + Contract)

- [x] Data Categories מפורטות

- [x] Retention Periods מפורטים

- [x] Third Parties מפורטים (Slack, AWS, SendGrid)

- [x] Contact DPO מפורט

Article 17 — Right to Erasure

- [x] "Delete My Data" Button במשתמש Settings

- [x] Deletion מבוצע תוך 30 יום

- [x] Audit Log: שם משתמש מוחלף ב-"[Deleted User]"

- [ ] Deletion מה-Email Provider (SendGrid) — Pending

Article 28 — Data Processing Agreement

- [x] DPA חתום עם AWS

- [x] DPA חתום עם Slack

- [x] DPA חתום עם SendGrid

- [ ] DPA עם ארגוני לקוחות — Template מוכן, טרם הופץ

Article 32 — Security of Processing

- [x] Encryption at rest (AES-256)

- [x] Encryption in transit (TLS 1.3)

- [x] Access Control (RBAC)

- [x] Backup Encryption

- [x] Incident Response Plan

Data Residency

- [x] EU Data: AWS eu-west-1 (Ireland)

- [x] US Data: AWS us-east-1 (Virginia)

- [x] Customer Can Choose Region at Signup[28][29][30][31][32]

📄 מסמך 8.2 — NDA Template לפרויקט

כותב: Legal
מיועד ל: כל Vendor/Contractor חיצוני
מתי: לפני כל שיתוף מידע עם צד שלישי

Non-Disclosure Agreement — TaskFlow

הצדדים: [Company Name] ("החברה") ו-[Vendor Name] ("הצד המקבל")

מה מוגדר כ-Confidential:

- Source Code, Algorithms, Database Schemas

- Product Roadmap, Pricing, Business Strategy

- Customer Data, User Research

- Technical Specifications, API Documentation

- Security Architecture

חובות הצד המקבל:

- שמירה על סודיות למינימום 5 שנים

- לא לשתף עם Sub-Contractors ללא אישור

- מחיקת מידע בתום ההסכם

- שמירה על Encrypted Systems בלבד

הגנה על IP:

- כל עבודה שנוצרה במסגרת ההסכם שייכת לחברה

- Work-for-Hire Clause

- No Reverse Engineering

שלב 9: Launch ועלייה לאוויר

📄 מסמך 9.1 — Go-Live Checklist

כותב: Engineering Lead + PM + DevOps
מיועד ל: כל צוותים
מתי: שבוע לפני Launch

TaskFlow — Go-Live Checklist v1.0
Launch Date: Week 14, Monday 10:00 AM UTC

Engineering Readiness

- [x] כל TC-Critical עוברים ב-Production Environment

- [x] Performance Test: 10K concurrent users — PASSED

- [x] Security: Pen Test issues תוקנו (0 Critical, 0 High)

- [x] SSL Certificate תקף ועד 2027

- [x] DNS Propagation מאומת

- [x] Database Backups אוטומטיים ב-6hr intervals

- [x] Rollback Plan תועד ונבדק

Monitoring & Alerting

- [x] AWS CloudWatch Dashboards פעילים

- [x] PagerDuty Alerts: API Error Rate > 1% → P1 Alert

- [x] Datadog APM פעיל

- [x] Uptime Monitor (Pingdom) — taskflow.io + api.taskflow.io

- [x] Error Budget: 99.9% SLO מוגדר ומנוטר

Deployment

- [x] Blue-Green Deployment מוגדר

- [x] Feature Flags מוכנים (Emergency Rollback)

- [x] Data Migration Script רץ בסביבת Staging ✓

Security Final

- [x] WAF Rules פעילים

- [x] Rate Limiting פעיל

- [x] HTTPS Redirect מ-HTTP

- [x] Security Headers בדקנו (securityheaders.com: A+)

Marketing Readiness

- [x] Landing Page Live — taskflow.io

- [x] Email Sequences מוכנות ב-SendGrid

- [x] Press Release מוכן לשליחה

- [x] Social Media Posts מוכנים ומוזמנים

Legal

- [x] Privacy Policy ו-Terms of Service Live

- [x] GDPR Banner פעיל

- [x] DPA Template מוכן לשליחה ללקוחות

Support

- [x] Intercom מוגדר

- [x] Help Center — 15 Articles פורסמו

- [x] On-Call Rotation להשבוע הראשון: 24/7

- [x] Escalation Path מוגדר[33][34][35][36][37]

📄 מסמך 9.2 — Runbook (Deployment Runbook)

כותב: DevOps + Engineering Lead
מיועד ל: On-Call Engineer
מתי: Launch Day + כל Deployment עתידי

TaskFlow — Production Deployment Runbook v1.0

Pre-Deployment (T-2 שעות)

# 1. Verify staging is healthy
curl -s https://staging.taskflow.io/health | jq .

# 2. Run final test suite
npm run test:e2e:staging

# 3. Tag release
git tag v1.0.0 && git push origin v1.0.0

# 4. Notify team
slack-notify "🚀 TaskFlow v1.0.0 deployment starting in 2hrs"

Deployment Steps (T-0)

# 1. Deploy to Production (Blue-Green)
aws ecs update-service --cluster taskflow-prod \
  --service taskflow-api --force-new-deployment

# 2. Monitor rollout
watch -n 5 'aws ecs describe-services --cluster taskflow-prod \
  --services taskflow-api | jq .services.deployments'

# 3. Smoke Tests
./scripts/smoke-test-production.sh

# 4. Shift traffic (Blue → Green)
aws elbv2 modify-listener --listener-arn $LISTENER_ARN \
  --default-actions Type=forward,TargetGroupArn=$GREEN_TG_ARN

Rollback Procedure (אם צריך)

# Immediate rollback (< 5 minutes)
aws elbv2 modify-listener --listener-arn $LISTENER_ARN \
  --default-actions Type=forward,TargetGroupArn=$BLUE_TG_ARN

# Notify team
slack-notify "⚠️ TaskFlow rollback executed — investigating"

Incident Response

| אינדיקטור | Threshold | פעולה |
| --- | --- | --- |
| Error Rate | > 1% | Page on-call engineer |
| API Latency P99 | > 2s | Investigate, consider rollback |
| DB CPU | > 80% | Scale up RDS immediately |
| Memory | > 90% | Scale ECS tasks |

📄 מסמך 9.3 — GTM (Go-To-Market) Document

כותב: Product Marketing Manager + VP Marketing
מיועד ל: Sales, Marketing, PR, CS
מתי: 4 שבועות לפני Launch

TaskFlow — GTM Launch Plan v1.0

Launch Tiers

| Layer | תיאור | Budget |
| --- | --- | --- |
| Tier 1 (Core) | PR + Blog + Email to Waitlist | 8K$ |
| Tier 2 (Paid) | LinkedIn Ads + G2 Review Campaign | 22K$ |
| Tier 3 (Events) | Webinar + Product Hunt Launch | 5K$ |

Messaging Architecture

Primary Message:

"TaskFlow — The only task manager built inside Slack. Hand off work in one click, never lose track again."

For CS Teams:

"Stop chasing updates across tools. TaskFlow lives in Slack, where your team already works."

For Managers:

"See every task status in real-time — no more 'where does this stand?' messages."

Launch Timeline

| תאריך | פעילות | בעלים |
| --- | --- | --- |
| T-4 שבועות | Waitlist Email #1 — "We're almost ready" | Marketing |
| T-3 שבועות | Blog Post: "Why Task Handoffs Break Teams" | Content |
| T-2 שבועות | Press Outreach (TechCrunch, Product Hunt) | PR |
| T-1 שבוע | Beta Customer Case Study Published | PMM |
| Launch Day | Product Hunt Launch 00:01 AM | Marketing |
| Launch Day | Email Blast לכל Waitlist (3,200 נרשמים) | Marketing |
| Launch Day | LinkedIn Video + Slack Communities | Social |
| T+1 שבוע | Webinar: "TaskFlow Demo + Q&A" | PM + Marketing |
| T+2 שבועות | Retargeting Campaign | Paid |

First 30 Days KPIs

- 500 New Signups

- 100 Activated Organizations (at least 3 Tasks created)

- 30 Paying Organizations

- 5 Customer Reviews on G2

- NPS > 35[38][39][40][41][42]

שלב 10: לאחר ה-Launch

📄 מסמך 10.1 — Post-Mortem Report

כותב: PM + Engineering Lead
מיועד ל: All Teams
מתי: שבוע 2 לאחר Launch

TaskFlow — Launch Post-Mortem
"What happened, what we learned, what we're changing"

Timeline

| שעה | אירוע |
| --- | --- |
| 00:01 | Product Hunt Published |
| 08:30 | Email Blast נשלח — 3,200 נמענים |
| 09:15 | Traffic spike — 850 concurrent users |
| 09:22 | INCIDENT: API latency > 5s |
| 09:35 | On-call engineers paged |
| 09:50 | Identified: RDS Connection Pool exhausted |
| 10:05 | Fix: Increased Max Connections + Added PgBouncer |
| 10:15 | API back to normal latency |
| Total downtime | 53 minutes degraded performance |

What Went Well

- Product Hunt: #3 Product of the Day 🏆

- 892 Signups ביום הראשון (Target: 100)

- CS Team Response Time < 2hr לכל Ticket

- Feature Flags worked perfectly — no rollback needed

What Went Wrong

- DB Connection Pool לא Scale עם Traffic Spike

- Alert fired 15 minutes too late (Threshold גבוה מדי)

- Slack notification flood — 400 users unsubscribed

Root Causes

- Load Testing לא כלל Spike Scenario (רק Steady Load)

- Alert Threshold הוגדר ל-P99 > 5s, צריך להיות P95 > 2s

Action Items

| פריט | בעלים | Due | Priority |
| --- | --- | --- | --- |
| הוסף Spike Test ל-CI | DevOps | Sprint 7 | High |
| הורד Alert Threshold ל-P95 > 1s | DevOps | Week 1 | Critical |
| הוסף PgBouncer לכל Environments | Engineering | Week 1 | Critical |
| Review Notification Frequency | PM | Week 2 | Medium |

📄 מסמך 10.2 — OKR Review (Quarter End)

כותב: PM + VP Product
מיועד ל: Leadership Team
מתי: סוף הרבעון הראשון לאחר Launch

TaskFlow — OKR Review Q1 Post-Launch

Objective: Launch TaskFlow and Achieve Initial Product-Market Fit

| Key Result | Target | Actual | ביצוע | סטטוס |
| --- | --- | --- | --- | --- |
| 200 Paying Orgs ב-6 חודשים | 200 | 312 | 156% | ✅ Exceeded |
| NPS > 40 | 40 | 47 | 117% | ✅ Exceeded |
| Churn < 5%/month | 5% | 2.8% | 144% | ✅ Exceeded |
| MAU/Registered > 80% | 80% | 71% | 89% | ⚠️ At Risk |
| Support Ticket Rate < 2% | 2% | 3.4% | — | ❌ Missed |

Insights

הביצוע ב-Paying Orgs מדהים (+56% מעל Target). ה-Support Ticket Rate גבוה — הסיבה העיקרית: Onboarding לא מספיק ברור לOrganization Admin. Q2 תוקן עם Guided Onboarding.

📊 מטריצת מסמכים מלאה

| מסמך | שלב | כותב | זמן כתיבה | משך שימוש |
| --- | --- | --- | --- | --- |
| Product Brief | 1 | PM | 2–4 שעות | כל הפרויקט |
| User Research Report | 1 | UX Research | 1–2 שבועות | Discovery → Design |
| Competitive Analysis | 1 | PMM | 1 שבוע | Discovery → GTM |
| Business Case | 2 | PM + Finance | 3–5 ימים | Budget Approval |
| Headcount Request | 2 | HR + PM | 1–2 ימים | Hiring Process |
| PRD | 3 | PM | 1–2 שבועות | כל הפרויקט (Living Doc) |
| BRD | 3 | PM + BA | 3–5 ימים | Executive Reference |
| SRS | 3 | Engineering + PM | 1–2 שבועות | Engineering Reference |
| ADR | 3 | Engineering | שעות לכל ADR | Long-term Reference |
| Design Spec | 4 | Designer | 2–3 שבועות | Development Reference |
| Sprint Plan | 5 | Engineering + PM | 2–4 שעות | Per Sprint (2 שב') |
| DoD | 5 | Engineering | 1–2 שעות | כל ה-Sprint |
| Code Review Checklist | 5 | Engineering Lead | 1–2 שעות | כל PR |
| Test Plan | 6 | QA | 1 שבוע | Testing Phase |
| Bug Report | 6 | QA | 15–30 דקות/באג | Testing → Fixed |
| UAT Report | 6 | PM + QA | 1 שבוע | Pre-Launch Decision |
| Threat Model | 7 | Security | 1–2 שבועות | Security Review |
| Pen Test Report | 7 | External | External | Pre-Launch |
| GDPR Checklist | 8 | Legal + Engineering | 1–2 שבועות | Compliance |
| NDA | 8 | Legal | 1–2 שעות/NDA | Per Vendor |
| Go-Live Checklist | 9 | Engineering + PM | 1 שבוע | Launch Day |
| Runbook | 9 | DevOps | 2–3 ימים | Launch + Ongoing |
| GTM Document | 9 | PMM | 2–3 שבועות | Launch Campaign |
| Post-Mortem | 10 | PM + Engineering | 1–2 ימים | Learning |
| OKR Review | 10 | PM + Leadership | 2–4 שעות | Quarterly |

סה"כ: 25 מסמכים מרכזיים | 9 שלבים | 14 מחלקות מעורבות | ~160 ימי עבודה

References

- A Complete Guide to Discovery Phase in Software Development - Explore the critical steps in the software discovery phase: insights, best practices, and tips to tu...

- The Project Discovery Phase in Software Development: Full Guide - Project discovery phase deliverables include SRS, prototypes, market analysis, technical documentati...

- Securing a Solid IT Budget: ROI, Risks, and Business Priorities - Learn how to build a solid IT budget proposal with ROI, risk management, and business priorities to ...

- Technical Project ROI Templates: The Complete Guide ... - Full Scale - Technical project ROI evaluation matters more now than ever before. Companies struggle to justify te...

- ROI of IT projects: 3-step calculation example - AEB - In today’s dynamic markets, you must invest in IT. But to get budget approval, you need the ROI. We ...

- Essential onboarding documents for new hires - Support your new hires with these essential onboarding documents that standardize and optimize your ...

- Complete Onboarding Checklist for New Technical Hires (Free Template) - Streamline your onboarding process for new technical hires with a comprehensive checklist covering p...

- Product Requirements Document (PRD) Template - Comprehensive PRD template with sections for features, user stories, acceptance criteria, and techni...

- Free Product Requirement Document (PRD) Templates - Smartsheet - Download free, customizable product requirement templates and examples in Excel, Microsoft Word, and...

- Free PRD Template: Guide to Product Requirements Documents - Download our PRD template and learn to create a document that drives alignment, avoids mistakes, and...

- Product Requirements Document: PRD Templates and Examples - A PRD describes what capabilities are expected from the final product from the perspective of the en...

- The Most Common Requirements Documents and How to Use Them - Discover the importance of using the right requirements documents for your project's success. Our gu...

- BRD vs. SRS: Demystifying Two Key Project Documents - Digital Code - BRD: Focuses on the broader business context, defining the overall project scope. SRS: Concentrates ...

- Software Testing Documentation: FRS, SRS, BRS & Other ... - TestFort - In this article, we're going to look at the three main document types that focus on the anticipated ...

- Vision to Blueprint: Complete Guide to BRD, FRD, SRS & TDD - Transform your software vision into a concrete blueprint! In this comprehensive guide, I'll walk you...

- Engineering Design Doc | Zoom Gallery

- Technical Design Template - Devplan - Next generation product development planning.

- FREE Technical Documentation Template | Collaborative Specs - Miro - Create collaborative technical documentation that teams actually read. Use Miro's template with AI t...

- Definition of done (DoD) in Agile: Meaning and examples - Wrike - Learn what definition of done (DoD) means in Agile and Scrum, why it matters, examples, benefits, an...

- Why Use a Definition of Done in an Agile Project?

- Understanding the Definition of Done: What it Means and ... - ICAgile - For agile teams, a Definition of Done identifies the criteria that a task, feature, or user story mu...

- The Definition of Done in Scrum | Agile Academy - The Definition of Done (DoD) is an Agreement between Team members. It is a scrum artefact, that help...

- Talent500https://talent500.comDefinition of Done Guide for Agile & Scrum Teams - Talent500 - Discover what the Definition of Done (DoD) means in Agile and Scrum, its importance for project qual...

- [PDF] Integrating Threat Modeling into the Development Lifecycle - ICCK

- Threat Modeling Process | OWASP Foundation - Threat Modeling Process on the main website for The OWASP Foundation. OWASP is a nonprofit foundatio...

- What is Secure SDLC (SSDLC)? - Cobalt - Learn how integrating security into every stage of the Software Development Lifecycle (SDLC) helps e...

- Secure Software Development Lifecycle

- Outsourcing Software Development? The Executive Checklist for IP ... - Discover a comprehensive, executive-level checklist to protect your intellectual property when outso...

- Custom Software Development Legal & Contract Checklist (US) - Custom software contract checklist for US deals: spot red flags in MSA, SOW, SLA, and DPA, then nego...

- Non-Disclosure Agreements: Your Quick Guide to NDAs - Sirion - A non-disclosure agreement is a business contract that protects data, ideas, and other sensitive inf...

- Software Development Agreement Checklist - Rikkeisoft - 1. Services and resources to be provided · 2. Deliverables and Acceptance Criteria · 3. Pricing and ...

- Software Development Agreement Checklist - nCube - Here are the main agreements that protect a client's Intellectual Property during the software devel...

- Software Deployment In 2026: 7 Strategies & 5 Steps With Checklist - Enable application monitoring; Track performance metrics; Set up error logging and alerts; Apply pat...

- Go-live planning checklist: 70 essential tasks to ensure ... - A go-live checklist is a structured document tracking all tasks, dependencies, and sign-offs require...

- Use the go-live checklist to make sure your solution is ready - Dynamics 365 - The go-live checklist helps you assess the readiness, completeness, and quality of your solution and...

- Your Ultimate 8-Point Deployment Checklist for 2025 - resolution - Don't let your next launch fail. Use our comprehensive 8-point deployment checklist to ensure a smoo...

- Software Deployment Best Practices for Modern Engineering Teams - Your Software Deployment Checklist; Consider a Canary Deployment Strategy; Maintain a Robust Rollbac...

- GTM Product Launch Template | Miroverse - Discover how Sidhant Ahluwalia does GTM Product Launch in Miro with Miroverse, the Miro Community Te...

- The GTM Product Launch Strategy Checklist for 2026 - Highspot - Planning, executing, and optimizing your B2B product launch strategy with an AI sales enablement pla...

- Product launch brief template - Product-led Hub - Increase revenue, cut costs, and reduce risk with Pendo's Software Experience Management platform. O...

- What is a Go-to-Market Strategy? GTM Plan Template + Examples - See how one serial entrepreneur tackles creating GTM plans that drive customer intrigue.

- FREE Go-To-Market Plan & Strategy Template - This template is an all-in-one tool for a successful product launch. It guides you through every ste...